## Team
Initials | First | Last | Email | GitHub Username
WX | Weipu | Xu | wxu16@stevens.edu | sumuruhala(sumuruvep)
ZL | Zheng | Li | zli71@stevens.edu | DaLaoL1
GL | Gaojie | Li | gli12@stevens.edu | Gaojie-Li
|  |  | GitHub Repository: | SSW555Project | https://github.com/Gaojie-Li/SSW555Project/commits/master

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US03 | Birth before death | ZL | Done
1 | US02 | Birth before marriage | GL | Done
1 | US01 | Dates before current date | WX | Done
1 | US06 | Divorce before death | GL | Done
1 | US05 | Marriage before death | ZL | Done
1 | US04 | Marriage before divorce | WX | Done
2 | US08 | Birth before marriage of parents | GL | Done
2 | US29 | List deceased | ZL | Done
2 | US28 | Order siblings by age | WX | Done
2 | US09 | Birth before death of parents | GL | Done
2 | US22 | Unique IDs | ZL | Done
2 | US41 | Include partial dates | WX | Done
3 | US11 | No bigamy | GL
3 | US35 | List recent births | ZL
3 | US34 | List large age differences | WX | Done
3 | US30 | List living married | GL
3 | US36 | List recent deaths | ZL
3 | US13 | Siblings spacing | WX | Done
4 | US38 | List upcoming birthdays | GL | Planning
4 | US17 | No marriages to descendants | ZL | Planning
4 | US18 | Siblings should not marry | WX | Planning
4 | US39 | List upcoming anniversaries | GL | Planning
4 | US16 | Male last names | ZL | Planning
4 | US10 | Marriage after 14 | WX | Planning

## Burndown
Date | Planned Remaining Stories | Actual Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2018-02-12 | 24 | 24 |  | 0
2018-02-26 | 18 | 18 | 6 | 115 | 210 | 32.8571
2018-03-19 | 12 | 12 | 6 | 145 | 435 | 20
2018-04-02 | 6 | 6 | 6 | 180 | 400 | 27
2018-04-16 | 0 | 0 | 6 | 100 | 175 | 34.2857

## Sprint1
Story ID | Story Name | Owner | Status | Est Size(LOC) | Est Time(mins) | Act Size(LOC) | Act Time(mins) | Completed
2018-02-26
US01 | Dates before current date | WX | Done | 50 | 60 | 60 | 50 | 100%
T01.01 | Collect date in data | WX
T01.02 | Get current date | WX
T01.03 | Filter the invalid date | WX
US04 | Marriage before divorce | WX | Done | 40 | 50 | 26 | 30 | 100%
T04.01 | Marriage time | WX
T04.02 | Divorce time | WX
T04.03 | Compare and check 2 timeWX | WX
US03 | Birth before death | ZL | Done | 15 | 30 | 10 | 25
T03.01 | Store birth date | ZL | Done | 12 | 20 | 7 | 15
T03.02 | Store death date | ZL | Done | 12 | 20 | 7 | 15
T03.03 | Compare birth and death dates | ZL | Done | 3 | 10 | 3 | 10
US05 | Marriage before death | ZL | Done | 15 | 40 | 12 | 30
T05.01 | Find marriage record for individual | ZL | Done | 11 | 30 | 8 | 20
T05.02 | Find marriage date | ZL | Done | 11 | 30 | 8 | 20
T05.03 | Compare marriage date to birth date | ZL | Done | 4 | 10 | 4 | 10
US02 | Birth before marriage | GL | Done | 30 | 40 | 24 | 40
T02.01 | Extract birth date and mariage date for everyone
T02.02 | Compare those two dates
US06 | Divorce before death | GL | Done | 30 | 40 | 29 | 30
T06.01 | Extract divorce date if there is one for all dead person
T06.02 | Compare the date of the divorce and date of death to see valid or not
Things to keep:
Collaborating on online tools and github
Using VSCode
Scrum practices
Things to avoid:
We didn't using pair programming in implementing user stories for the first sprint which we should start using it for all future sprint.

## Sprint2
Story ID | Story Name | Owner | Status | Est Size(LOC) | Est Time(mins) | Act Size(LOC) | Act Time(mins) | Completed
2018-03-19
US28 | Order siblings by age | WX | Done | 100 | 120 | 33 | 100
T028.01 | Get ages | WX
T028.02 | Sort | WX
US41 | Include partial dates | WX | Done | 80 | 60 | 37 | 200
T041.01 | Get dates | WX
T041.02 | Include | WX
US31 | List living single | ZL | Done | 30 | 30 | 13 | 40
T22.01 | iterate all individual | ZL
T22.02 | check birth date and fams | ZL
US29 | List deceased | ZL | Done | 15 | 20 | 11 | 35
T29.01 | determine sort standard | ZL
T29.02 | sort | ZL
US08 | Birth before marriage of parents | GL | Done | 50 | 60 | 23 | 30
T08.01 | Extract birth date
T08.02 | Extract parents marriage date
T08.03 | Compare two dates
US09 | Birth before death of parents | GL | Done | 50 | 60 | 28 | 30
T09.01 | Extract birth date
T09.02 | Extract death dates for both parents
T09.03 | Compare all dates
Things to keep:
Lean: Stop and fix/improve code of current user stories before beginning next stories
Collaborating on online tools and github
Using VSCode
Scrum practices
Things to avoid:
Lean wastes on planning: needs do what customers directly asked for or internal features that only prerequisited by following user stories

## Sprint3
Story ID | Story Name | Owner | Status | Est Size(LOC) | Est Time(mins) | Act Size(LOC) | Act Time(mins) | Completed
2018-04-02
US34 | List large age differences | WX | Done | 30 | 60 | 30 | 80
T034.01 | Get age of both husband and wife in every family | WX
T034.02 | Compare the age to find the difference | WX
US13 | Siblings spacing | WX | Done | 25 | 60 | 34 | 100
T013.01 | Get birth date info | WX
T013.02 | Checking | WX
US11 | No bigamy | GL | Done | 50 | 60 | 33 | 50
T11.01 | Extract all FAMS information
T11.02 | Compare their marry date and divorce date
T11.03 | Check whether any dates overlapped
US30 | List living married | GL | Done | 30 | 60 | 11 | 30
T30.01 | Get Birth, Death, Marry info for everyone
T30.02 | List all ppl who has already married
US35 | List recent births | ZL | Done | 25 | 60 | 36 | 70
T35.01 | Get birth date for everyone
T35.02 | Calculate days
US36 | List recent deaths | ZL | Done | 25 | 60 | 36 | 70
T36.01 | Get death date if exists
T36.02 | Calculate days
Things to keep:
Using VSCode and GitHub
Efficient communication between team members
Things to avoid:
We think we are all in pretty good shape :)))

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
2018/4/--
US18 | Siblings should not marry | WX | Done | 50 | 100 | 20 | 30
US10 | Marriage after 14 | WX | Done | 30 | 60 | 24 | 35
US33 | List orphans | GL | Done | 60 | 100 | 23 | 30
T33.01 | Find everyone with 'FAMC' entry
T33.02 | Check their birth date
T33.03 | Check their parents living or not
T33.04 | Output indivisual satisfying the condition
US21 | Correct gender for role | GL | Done | 40 | 50 | 10 | 30
US21.01 | Check all individuals with 'FAMS' entry
US21.02 | Check their gender and their role in the family
US21.03 | Report all un-corresponding entries
US12 | Parents not too old | ZL | Done | 30 | 30 | 14 | 30
US12.01 | Find parents' ids with 'FAMC' entry
US12.02 | Get parents' birthdays in individual dictionary
US12.03 | Compare every birthday with the child
US16 | Unique name and birth date | ZL | Done | 30 | 30 | 9 | 20
US16.01 | Iterate all members in individual dictionary
US16.02 | Skip the same Id with input id
US16.03 | Check everyone's name and birthday
Things to keep:
Using VSCode and GitHub
Efficient communication between team members
Things to avoid:
We think we are all in pretty good shape :)))

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)